## JD Index
ID | Category | Area | Locations | Notes
10.10 Project Charter | 10 Integration | 10-19 PMP | Filesystem | Formal authorisation for the existence of the project and the project manager's authorisation to apply organisational resources to the project activities.
10.20 Project Management Plan | 10 Integration | 10-19 PMP | Filesystem | How the project will be executed, monitored, controlled and closed.
10.21 Project Lifecycle Description | 10 Integration | 10-19 PMP | OneNote | Description of the basic framework and phases the project will pass through.
10.22 Project Development Approach | 10 Integration | 10-19 PMP |  | Description of the method used to create and evolve the product, service, or result during the project life cycle such as predictive, iterative, incremental, agile or a hybrid method.
10.23 Change Management Plan | 10 Integration | 10-19 PMP |  | Establishes the change control board, documents the extent of its authority and describes how the change control system will be implemented.
10.24 Configuration Management Plan | 10 Integration | 10-19 PMP |  | Describes how to identify and account for project artefacts under configuration control, and how to record and report changes to them.
10.25 Business Case | 10 Integration | 10-19 PMP |  | The documented economic feasibility study used to establish validity of the benefits of the project used as the basis for the authorisation of further project management activities.
10.30 Change Log | 10 Integration | 10-19 PMP |  | A comprehensive list of changes submitted during the project and their current status.
10.31 Assumption Log | 10 Integration | 10-19 PMP | Filesystem | Record of all assumptions.
10.32 Constraints Log | 10 Integration | 10-19 PMP |  | Record of all constraints.
10.33 Issue Log | 10 Integration | 10-19 PMP |  | Record of all issues that may have an impact on the project objectives.
10.40 Lessons Learned Register | 10 Integration | 10-19 PMP |  | A list used to record knowledge gained during a project so that it can be used in the current project and entered into the lessons learned repository.
10.41 Lessons Learned Repository | 10 Integration | 10-19 PMP |  | A store of historical information about lessons learned in a project.
11.20 Scope Management Plan | 11 Scope | 10-19 PMP |  | Describes how the scope will be defined, developed, monitored, controlled and validated.
11.21 Project Scope Statement | 11 Scope | 10-19 PMP | OneNote | Description of the project scope, major deliverables, assumptions and constraints.
11.30 Requirements Management Plan | 11 Scope | 10-19 PMP |  | Describes how requirements will be analysed, documented and managed.
11.31 Requirements | 11 Scope | 10-19 PMP | Filesystem | A table of conditions or capabilities necessary to be present in the project work products.
11.32 Anecdote Log | 11 Scope | 10-19 PMP |  | Record of anecdotes collected during the lifecycle of the project that can be used during project closure to compare delivery success.
11.32 Requirements Traceability Matrix | 11 Scope | 10-19 PMP |  | A table that links requirements from their origin to the deliverables that satisfy them.
11.33 Client Quote | 11 Scope | 10-19 PMP | Filesystem | This is what was sold to the client
11.40 Work Breakdown Structure (WBS) | 11 Scope | 10-19 PMP |  | Hierarchical decomposition of the total scope of work to be carried out to accomplish the project objectives and create the required deliverables.
11.41 WBS Dictionary | 11 Scope | 10-19 PMP | Filesystem | Detailed deliverable, activity and scheduling information about each component in the WBS.
12.20 Schedule Management Plan | 12 Schedule | 10-19 PMP |  | Establishes the criteria and the activities for developing, monitoring and controlling the schedule.
12.21 Schedule Model | 12 Schedule | 10-19 PMP |  | A representation of the plan for executing the project's activities including durations, dependencies and other planning information that can be used to produce a schedule.
12.22 Project Schedule | 12 Schedule | 10-19 PMP | Filesystem | The output of the schedule model that presents linked activities with planned dates, durations, milestones and resources.
12.23 Milestone List | 12 Schedule | 10-19 PMP |  | A table of the significant points or events in the project.
12.24 Project Calendar | 12 Schedule | 10-19 PMP |  | Identifies working days and shifts that are available for scheduled activities.
12.25 Schedule Forecasts | 12 Schedule | 10-19 PMP |  | Estimates or predictions of conditions and events in the project's future based on information and knowledge available at the time the schedule is calculated.
12.31 Activity List | 12 Schedule | 10-19 PMP |  | A table of schedule activities showing activity description, activity identifier and detailed work descriptions of the work to be performed.
12.32 Duration Estimates | 12 Schedule | 10-19 PMP |  | Quantitative assessments of the likely number of time periods required to complete an activity, phase or project.
12.33 Basis of Estimates | 12 Schedule | 10-19 PMP |  | Supporting documentation outlining the details used in establishing project estimates such as assumptions, constraints, level of detail, ranges and confidence levels.
13.10 Customer Purchase Order | 13 Cost | 10-19 PMP | Filesystem
13.20 Cost Management Plan | 13 Cost | 10-19 PMP |  | Describes how costs will be planned, structured, and controlled.
13.30 Budget | 13 Cost | 10-19 PMP |  | The approved estimate for the project or any work breakdown structure component or any schedule activity.
13.31 Cost Estimates | 13 Cost | 10-19 PMP |  | Quantitative assessments of the probable costs required to complete the project work as well as contingency amounts to account for identified risks and management reserve to cover unplanned work.
13.32 Cost Reporting | 13 Cost | 10-19 PMP | Filesystem
13.40 Cost Forecasts | 13 Cost | 10-19 PMP |  | The calculated EAC values documented and communicated to stakeholder.
14.20 Quality Management Plan | 14 Quality | 10-19 PMP |  | Describes how applicable policies, procedures and guidelines will be implemented to achieve the quality objectives.
14.21 Quality Metrics | 14 Quality | 10-19 PMP |  | Descriptions of work product attributes and how to measure it.
14.22 Test and Evaluation Documents | 14 Quality | 10-19 PMP |  | Description of the activities used determine if the work products meet the quality objectives.
14.30 Quality Control Measurements | 14 Quality | 10-19 PMP |  | The documented results of quality control activities.
14.31 Quality Reports | 14 Quality | 10-19 PMP |  | A record of quality management issues, recommendations for corrective actions and a summary of findings from quality control activities, including recommendations for improvements.
15.20 Resource Management Plan | 15 Resource | 10-19 PMP |  | Describes how project resources are acquired, allocated, monitored and controlled.
15.21 Project Team Assignments | 15 Resource | 10-19 PMP | OneNote | Record of team members and their roles and responsibilities for the project.
15.22 Physical Resource Assignments | 15 Resource | 10-19 PMP |  | Records of the material, equipment, supplies, locations and other physical resources used during the project.
15.23 Team Charter | 15 Resource | 10-19 PMP |  | Establishes the team values, agreements, and operating guidelines for the team.
15.24 Resource Calendars | 15 Resource | 10-19 PMP |  | The availability of people, equipment, and material resources, and resource attributes, such as experience or skill levels.
15.30 Resource Breakdown Structure (RBS) | 15 Resource | 10-19 PMP |  | A hierarchical representation of resources by category and type.
15.31 Resource Requirements | 15 Resource | 10-19 PMP |  | The types and quantities of resources required for each activity in a work package.
15.32 Resource Onboarding | 15 Resource | 10-19 PMP | Filesystem | Information and forms for project team members to get access to required systems
15.33 Training Ceritficates | 15 Resource | 10-19 PMP | Filesystem
16.20 Communications Management Plan | 16 Communication | 10-19 PMP |  | Describes how, when and by whom information about the project will be administered and disseminated.
16.30 Project Communications | 16 Communication | 10-19 PMP |  | Communication artefacts required by stakeholders.
16.31 Meeting Minutes | 16 Communication | 10-19 PMP | OneNote | Records of all meetings held.
16.32 Status Reports | 16 Communication | 10-19 PMP | Filesystem / VERA
17.20 Risk Management Plan | 17 Risk | 10-19 PMP |  | Describes how risk management activities will be structured and performed.
17.31 Risk Register | 17 Risk | 10-19 PMP | Filesystem | A table in which outputs of risk management processes are recorded.
17.32 Risk Report | 17 Risk | 10-19 PMP |  | Summary of information on individual project risks and the level of overall project risk.
18.20 Procurement Management Plan | 18 Procurement | 10-19 PMP |  | Describes how the project team will acquire goods and services from outside of the performing organisation.
19.20 Stakeholder Engagement Plan | 19 Stakeholder | 10-19 PMP |  | Identifies the strategies and actions required to promote productive involvement of stakeholders in project or program decision making and execution.
19.21 Stakeholder Register | 19 Stakeholder | 10-19 PMP | Filesystem | A table including the identification, assessment, and classification of project stakeholders.
20.10 PMF IWP Renewal | 20 Contract | 20-29 Client Data
21.11 Customer Budget Artecfacts | 21 Financial | 20-29 Client Data | Filesystem | Artefacts that include budget or cost
22.10 Customer Scope Artefacts | 22 Project Management | 20-29 Client Data | Filesystem | Artefacts that include requirements, scope, or constraints
22.12 Customer Systems Access | 22 Project Management | 20-29 Client Data | Filesystem
22.20 Glossary | 22 Project Management | 20-29 Client Data | OneNote
23.10 Office Templates | 23 Templates | 20-29 Client Data
30.10 High Level Design | 30 Internal Working | 30-39 Deliverables | Filesystem
30.11 Work Instructions and Sample Data | 30 Internal Working | 30-39 Deliverables | Filesystem
30.12 Report Draft Materials | 30 Internal Working | 30-39 Deliverables | Filesystem | Report Draft Working Folder
31.10 Milestone Deliverables | 31 Deliver to Client | 30-39 Deliverables | Filesystem / Objective
31.11 Overview Documentation | 31 Deliver to Client | 30-39 Deliverables | Filesystem